## Product Launch Plan
Product Launch Plan for |  | PRODUCT NAME
Project Details |  |  | Important Milestones |  | Team & Responsibilities
Project Start |  | 00.00.00 | End of Development | 00.00.00 | PM
Product Launch Date |  | 00.00.00 | Regulatory Approval | 00.00.00 | Marcom
|  |  | Field Test | 00.00.00 | Development
Pre-Launch Phase |  | 2 months | Start Promotion | 00.00.00 | Regulatory
Launch Phase |  | 1 month | Inventory / Stock | 00.00.00 | Production
Post-Launch Phase |  | 3 months | Sales Start | 00.00.00 | Operations
Code | Phase | Category | Task / Item |  | PM | Marcom | Sales | Development | Regulatory | Production | Operations | Service | N.N. | Start | Deadline | Status | Budget | Status
on schedule
1 | Pre-Launch | Product | Testing (QA & Acceptance) |  | x |  |  | x | x | [6 empty] | not yet started |  | at risk
2 | Pre-Launch | Product | Determine Product Name, Check Trademark Protection |  | x | [10 empty] | on schedule |  | delayed
3 | Pre-Launch | Product | Operating Manual EN/DE and Labeling |  | x |  |  |  | x | [6 empty] | at risk |  | done
4 | Pre-Launch | Product | Required Documentation for Regulatory Approval |  |  |  |  | x | x | [6 empty] | on schedule |  | not yet started
5 | Pre-Launch | Product | Other Required Documentation (tbd) |  |  |  |  | x | x | [6 empty] | not yet started
6 | Pre-Launch | Product | Define Packaging |  | x |  |  |  | x | x | x |  |  |  |  | done
7 | Pre-Launch | Product | Conduct Field Test with Lead User, KOL |  | x |  | x | x | x | [6 empty] | at risk
8 | Pre-Launch | Product | Production Planning, Supply Inventory |  | x |  |  |  |  | x | x |  |  |  |  | delayed
9 | Pre-Launch | Product | Final Product Approval (Review Board) |  | x |  |  | x | x | [6 empty] | delayed
10 | Pre-Launch | Product | Create Master Data | [7 empty] | x |  |  |  |  | on schedule
11 | Pre-Launch | Pricing | Summary of Costs | [6 empty] | x | [5 empty] | done
12 | Pre-Launch | Pricing | Calculation of Manufacturing Costs | [6 empty] | x | [5 empty] | done
13 | Pre-Launch | Pricing | Definition of (Transfer) Price |  | x | [5 empty] | x |  |  |  |  | done
14 | Pre-Launch | Sales | Sales Strategy, Global Roll-out Plan, Prios |  | x |  | x
15 | Pre-Launch | Sales | Identify Sales Channels and Distribution Partners |  |  |  | x
16 | Pre-Launch | Sales | Sales Programs, KOL Programs, Reference Customer Programs |  | x | x | x
17 | Pre-Launch | Sales | Sales Information & Training (Sales, Customer Support, Hotline, Service) |  | x |  | x |  |  |  |  | x |  |  |  | done
18 | Pre-Launch | Sales | Describe and Provide Value Proposition, USPs, Argumentation, Elevator Pitch |  | x | x | x |  | x | [6 empty] | not yet started
19 | Pre-Launch | Sales | Competitor Comparison |  | x |  | x | [8 empty] | done
20 | Pre-Launch | Sales | Provide Samples and Demokits, Define Product Presentation, Sales Tools |  | x |  |  | x |  | x | x |  |  |  |  | not yet started
21 | Pre-Launch | Marcom | Define Product Description & Messaging, Campaign Creation |  | x | x | [9 empty] | not yet started
22 | Pre-Launch | Marcom | Foto & Video Shooting |  | x | x
23 | Pre-Launch | Marcom | Provide Sample Quotes & TCO / ROI Calculation |  | x | x | x | [8 empty] | not yet started
24 | Pre-Launch | Marcom | Communication Plan (PR, Media, Social Media), Advertising Plan |  |  | x | [9 empty] | not yet started
25 | Pre-Launch | Marcom | Website, Microsite, Landing Page |  |  | x | [9 empty] | not yet started
26 | Pre-Launch | Marcom | Create Print Media (Brochure, Flyer) |  | x | x |  |  | x | [6 empty] | not yet started
27 | Pre-Launch | Marcom | Plan, Coordinate and Conduct Translations |  |  | x | x |  | x | [6 empty] | not yet started
28 | Pre-Launch | Marcom | Plan & Create Video, Animation, other Sales Tools (VR, Cheat Sheet, Demo Kit) |  | x | x | [9 empty] | not yet started
29 | Pre-Launch | Marcom | Plan & Organise Sales Training (also for Distribution Partners) |  | x | x | x | [8 empty] | not yet started
30 | Pre-Launch | Marcom | Plan & Organise Launch Event or Event Series, Roadshows etc. |  | x | x
31 | Launch | Marcom | Internal Launch, Internal Announcement |  | x | x | x | x | x | x | x | x
32 | Launch | Marcom | Final Announcement (Newsletter, Press Release, Social Media, Event) |  | x | x | [9 empty] | not yet started
33 | Launch | Sales | Product Demos at Customers (Key User, Mulitpliers) & Collect Feedback |  | x |  | x | [8 empty] | not yet started
34 | Post-Launch | Product | Lessons Learned, Project Evaluation |  | x | x | x | x | x | x | x |  |  |  |  | not yet started
35 | Post-Launch | Product | Complaint Management |  |  |  | x |  | x | [6 empty] | not yet started
36 | Post-Launch | Sales | Provide Application Training |  | x |  | x | [8 empty] | not yet started
37 | Post-Launch | Sales | Provide Sales Support, Q&A Sessions, Training |  | x |  | x | [8 empty] | not yet started
38 | Post-Launch | Marcom | Internal Communication, Intranet, Chats |  | x | x | [9 empty] | not yet started
39 | Post-Launch | Marcom | Congresses, Workshops, Events, Roadshows |  | x | x | x | [8 empty] | not yet started
40 | Post-Launch | Marcom | Create and Communicate References, Testimonials, Case Studies |  | x | x | x | [8 empty] | not yet started
41 | Post-Launch | Marcom | Create and publish additional content (scientifc articles, technology) |  | x | x |  | x | [7 empty] | not yet started
42 | Post-Launch | Marcom | Collect & Report Press Feedback & Clippings (Print, Online, Social Media) |  |  | x | [9 empty] | not yet started